## BPML
| Co-Packers -Kashipur |  | 2020-12-15
Module | Process Code | Process Name | Completion Date | Status
Co-packer | CP01 | RM/PM Procurement process | 2020-12-15 | BRD SignOff
Co-packer | CP02 | Potato Procurement process (Handling, Storage, Transfer) | 2020-12-15 | BRD SignOff
Co-packer | CP03 | Process for receipt, incoming quality, and storage/inventory management | 2020-12-15 | BRD SignOff
Co-packer | CP04 | Issuance of Raw material | 2020-12-15 | BRD SignOff
Co-packer | CP05 | Payment of RM PM | 2020-12-15 | Sumited For SignOff
Co-packer | CP06 | Reports | 2020-12-15 | WIP | HOLD
Co-packer | CP07 | Location Code | 2020-12-15 | Sumited For SignOff | HOLD
Co-packer | CP08 | Item Code | 2020-12-15 | Sumited For SignOff | HOLD
Co-packer | CP09 | Vendor Code | 2020-12-15 | Sumited For SignOff | HOLD
| BRD |  | 2020-12-30
Module | Process Code | Process Name | Completion Date
Purchase | DFM01 | RM/PM Process | 2020-12-30 | BRD SignOff
Stock | DFM02 | Process for receipt, incoming quality, and storage/inventory management | 2020-12-30 | BRD SignOff
Stock | DFM03 | INSURANCE OF RAW MATERIAL | 2020-12-30 | BRD SignOff
Accounts | DFM04 | Interigation with Tally | 2020-12-30 | Sumited For SignOff
Qualiy | DFM05 | Quality Check Process RM/PM | 2020-12-30 | Sumited For SignOff
Accounts | DFM06 | Accounts Process
Accounts | DFM07 | Cost Centre & Budgeting | Need to Discusstion
Manufactuering | DFM08 | Manifactuering | To be create
Quality | DFM09 | Quality Check Process WIP | Need to All items parameters
Admin | DFM10 | Enterpriseces Structre | Working
Support | DFM11 | Support Module | Working
Purchase | DFM12 | Indirect Purchase | Working
Interigation with SND
| Buying Module |  | 2021-01-31
Module | Process Code | Process Name | Completion Date
Buying |  | RM/PM Procurement process | 2021-01-31
| Quality Module |  | 2021-01-31
Module | Process Code | Process Name | Completion Date
Quality |  | Quality process Process | 2021-01-31
| Stock Module |  | 2021-01-31
Module | Process Code | Process Name | Completion Date
Stock |  | Inventory Management | 2021-01-31
| Support Module |  | 2021-03-01
Module | Process Code | Process Name | Completion Date
Support |  | Support Module | 2021-03-01
| Accounts Module |  | 2021-03-01
Module | Process Code | Process Name | Completion Date
Accounts |  | Account Module | 2021-03-01
| Manufacturing Module |  | 2021-03-15
Module | Process Code | Process Name | Completion Date
Manufacturing |  | Manufacturing Module | 2021-03-15
| Integration |  | 2021-03-15
Module | Process Code | Process Name | Completion Date
Integration |  | Integration like Tally / SND | 2021-03-15
| Testing Before Live |  | 2021-03-15
Module | Process Code | Process Name | Completion Date
Testing Before Live |  | Testing Before Live | 2021-03-15

## Sheet1
Group Company | Child Company | Warehouse/Store
DFM Foods | GN | RM
| GZB | Production
| HO | WIP
| Kashipur | FG
| CNF | Scrap
| Sale | Hold
Rejection
FIN BRD | Enterprisecs Structure
Subjects | GL/COA
Banking
Tax
Accounts Payable
Cash
Costing
Budgeting
Period Closer
Accounts Receable
Payroll Posting
Other Purhase BRD | Indirect
Subjects | Service
Consumable
Sub Contracting
QC | Quality | Incoming
In Process
Masters QC
Support | Customer Complain
Internal Tickets
Production | Masters | Workstation | Operation | Routing | BOM
| Prod Planing | SNOP
Material Plaining MRP
Work Order

## Sheet2
Task | Status
Greater Noida Procurment | Process Ready only Company to be create | 2021-01-21
GZB Procurment | Process Ready only Company to be create | 2021-01-21
Complete Procurment accounting | Testing Mode | 2021-01-21
Incoming Quality inspection | Need parameters for all items | 2021-01-21
Store and RM inventory management | Testing Mode | 2021-01-21
Tally inerface | Start working | 2021-01-28
HO Procurment | Process Ready only Company to be create
Budget Control for entire | Need to discussed with Finance team
Data Migration
Traiing
Opening Stock
Status of BBP Signoff
RM/PM Process | BRD SignOff
Process for receipt, incoming quality, and storage/inventory management | BRD SignOff
INSURANCE OF RAW MATERIAL | BRD SignOff
Interigation with Tally | Sumited For SignOff
Quality Check Process RM/PM | Sumited For SignOff
Accounts Process | Need More discussion
Cost Centre & Budgeting | Need More discussion
Indirect Purchase | Need More discussion
Manifactuering | Need More discussion
Quality Check Process WIP | Need More discussion
Enterpriseces Structre | Working
SND Integration | Need More discussion
Support Module | Need More discussion
Rolls Assignment
DFM Foods- Kolkata | Maurya Centre, Flat - 5D, Gariahat Road, Kolkata - 700019, West Bengal | 19AAACD1017B1ZF
DFM Foods Ltd.-GN-2/Proj-1 (Lease) | Plot No 2A, Sector 31, Ecotech - 1, Greater Noida, Distt Gautam Budh Nagar, Uttar Pradesh | 09AAACD1017B1ZG
DFM Foods Ltd- North Zone-1 | 8377 Roshanara Road Delhi 110007 | 07AAACD1017B1ZK
DFM Foods Ltd- North Zone-2 | 8377 Roshanara Road Delhi 110007 | 07AAACD1017B1ZK
DFM Foods Ltd- South | No. 108 Bidarahalli East, Taluka Virgonagar, Bangalore, Karnataka 560049 | 29AAACD1017B1ZE
DFM Foods Ltd- Mumbai | 49 H, 1st Floor, New Heaven Enterprise, Parasi Panchayat Road, Andheri (East), Mumbai - 400069, Maharashtra | 27AAACD1017B1ZI